## Gui
Feature	Estimation	Completed	For Level 2
Load Screen	3	X
Ending Screen	5
Status Menu	2	X
Party Menu	5		I'll have to add paging buttons, and in order to do party composition, I think I'll do something simpler like a swap button on the top three characters on the existing menu, rather than having a whole party composition menu
Item Menu	2	X
Equip Outcome Menu	2
Spell Menu	2
Buy Menu	2	X
Sell Menu	2	X
Use Menu	2	X
Save Menu	2

Total	29

## Field
Feature	Estimation	Completed	For Level 2
Recruiting	3		X
Enemy Orb	5			Different enemy groups have different dot colors (white = easiest, red = hardest).
Sealed Doors	2		X
Multiple Floors	3		X
Subtotal	13

Tomb / Town	Estimation	Completed
Recruitable NPCs	3		X
Inner Tomb Fire Pit	3
Subtotal	6

Data	Estimation	Completed
Armor Data	5
Accessory Data	5
Battle Data	5
Consumable Data	3
Shop Data	5
Weapon Data	5
Subtotal	28

Character	Estimation	Completed
Lead / Sword	3	X		Critical, Cyclone, Power Critical, Slash, Double Critical, Tornado, Tremor. Defending 50% more effective.
Brawler / Heavesword	3	X	X	Power Cut (Holy), Provoke Cut (Holy), Double Cut (Holy), Splash Cut (Holy), Triple Cut (Holy), Double Splash Cut (Holy), Provoke-X. Defending increases counter rate.
Wizard / Scythe	3		X	Flame Thrower, Lightning Bomb, Ice Crystal, Tidal Wave, Flame-X, Lightning-X, Ice-X, Water-X. Defending damage restore TP proportionately.
Cleric / Archer	3			Aura, Purify, Protect, Empower, Dispel, Numb, Weaken, Life. Defending damage restore TP proportionately.
Dimensionalist / Gunner	3			Slow, Haste, Slow-X, Haste-X, Summon Ifrit, Summon Shiva, Summon Lich, Summon Titan. Defending damage restore TP proportionately.
Assassin / Bare (N/A)	0	X		Physical attacker / steal / mixes two items, either doubles the power or produces a new effect (curative or offensive). Defending increases counter rate.
Subtotal	15

Level Designs	Estimation	Completed
Level 1 (Cave)	4	X
Level 2	4		X
Level 3	4
Level 4	4
Level 5	4
Level 6	4
Level 7	4
Level 8	4
Level 9	4
Subtotal	36

Total	98

## Battle
Feature	Estimation	Completed	For Level 2
Damage Flash	1
Buff Consumables	1		X
Tiled Background	1
Enemy Spawns	1		X
Enemy Drops	1		?
Counter Attacking	1		X
Subtotal	6

Effect	Estimation	Completed
Critical Strike	1	X
Cyclone	1	X
Slash	1	X
Bolt	1	X
Tremor	1
45 More Spells	45
Subtotal	5

Enemy	Estimation	Completed
Goblin	2.5	X
29 More Enemies	72.5
Subtotal	75

Total	86

## Deployment
Deployment	Estimation	Completed
Windows	10
iOS	10
Android	10

Total	30

## GrandTotal
Grand Total	243

## Bugs
Name	Priotiy (Very Low, Low, Medium, High, Very High)	Description
Character Diagonal Walk Animation Bug	Low
Characters Disappear Early	Low	Characters in battle disappear before the battle screen fades out.
Buy / Sell Excess Real Estate Graphic	Low
Graphics for Various Button Sizes	Low
Avatar is Horizontally Wider then Need Be	Medium	Either use two vertical circles or a pillbox instead.