## Gui
Feature	Estimation	Completed
Load Screen	3	X
Ending Screen	5
Status Menu	2	X
Party Menu	5
Item Menu	2	X
Equip Menu	2
Spell Menu	2
Buy Menu	2	X
Sell Menu	2	X
Use Menu	2	X
Save Menu	2

Total	29

## Field
Feature	Estimation	Completed
Recruiting	3
Enemy Orb	5
Sealed Doors	2
Multiple Floors	3
Subtotal	13

Tomb / Town	Estimation	Completed
Recruitable NPCs	3
Inner Tomb Fire Pit	3
Subtotal	6

Data	Estimation	Completed
Armor Data	5
Accessory Data	5
Battle Data	5
Consumable Data	3
Shop Data	5
Weapon Data	5
Subtotal	28

Character	Estimation	Completed
Lead	3	X
Brawler	3	X
Wizard	3
Cleric	3
Dimensionalist	3
Assassin	3
Subtotal	18

Level Designs	Estimation	Completed
Level 1 (Cave)	4	X
Level 2	4
Level 3	4
Level 4	4
Level 5	4
Level 6	4
Level 7	4
Level 8	4
Level 9	4
Subtotal	36

Total	101

## Battle
Feature	Estimation	Completed
Damage Flash	1
Buff Consumables	1
Tiled Background	1
Enemy Drops	1
Counter Attacking	1
Subtotal	5

Effect	Estimation	Completed
Critical Strike	1	X
Cyclone	1	X
Slash	1	X
Bolt	1	X
Tremor	1
45 More Spells	45
Subtotal	5

Enemy	Estimation	Completed
Goblin	2.5	X
29 More Enemies	72.5
Subtotal	75

Total	85

## Deployment
Deployment	Estimation	Completed
Windows	10
iOS	10
Android	10

Total	30

## GrandTotal
Grand Total	245

## Bugs
Name	Priotiy (Very Low, Low, Medium, High, Very High)	Description
Character Diagonal Walk Animation Bug	Low
Characters Disappear Early	Low	Characters in battle disappear before the battle screen fades out.
Buy / Sell Excess Real Estate Graphic	Low
Graphics for Various Button Sizes	Low
Avatar is Horizontally Wider then Need Be	Medium	Either use two vertical circles or a pillbox instead.