## Gui
Feature	Estimation	Completed
Load Screen	3	X
Ending Screen	5
Status Menu	2	X
Party Menu	5
Item Menu	2	X
Equip Menu	2
Spell Menu	2
Buy Menu	2	X
Sell Menu	2	X
Use Menu	2	X
Save Menu	2

Total	29

## Field
Feature	Estimation	Completed
Recruiting	3
Enemy Orb	5
Sealed Doors	2
Multiple Floors	3
Subtotal	13

Tomb / Town	Estimation	Completed
Recruitable NPCs	3
Inner Tomb Fire Pit	3
Subtotal	6

Data	Estimation	Completed
Armor Data	5
Accessory Data	5
Battle Data	5
Consumable Data	3
Shop Data	5
Weapon Data	5
Subtotal	28

Character	Estimation	Completed
Lead	3	X
Brawler	3	X
Wizard	3
Cleric	3
Dimensionalist	3
Assassin	3
Subtotal	18

Total	65

## Battle
Feature	Estimation	Completed
Damage Flash	0.5
Buff Consumables	1
Tiled Background	1
Enemy Drops	1
Counter Attacking	1
Subtotal	4.5

Effect	Estimation	Completed
Critical Strike	0.5	X
Cyclone	1	X
Slash	1	X
Bolt	1	X
Tremor	1
45 More Spells	45
Subtotal	4.5

Enemy	Estimation	Completed
Goblin	2.5	X
29 More Enemies	72.5
Subtotal	75

Total	84

## Deployment
Deployment	Estimation	Completed
Windows	10
iOS	10
Android	10

Total	30

## Total
Grand Total	208