## Gui
Feature	Estimation	Completed	For Level 2
Load Screen	3	X
Ending Screen (Good)	5
Ending Screen (Bad)	5
Credits Menu	2	>
Status Menu	2	X	X
Party Menu	5	>	X	In order to do party composition, I think I'll do something simpler like a swap button on the top three characters on the existing menu, rather than having a whole party composition menu
Item Menu	2	X	X	Need also to group items and display number owned.
Options Menu	2			Battle Speed: Slow | Normal | Fast | Wait; Quit to Main Menu
Equip Outcome Menu	2
Tech Menu	2	>	X
Buy Menu	2	X	X
Sell Menu	2	X	X
Use Menu	2	X	X

Total	36

## Field
Feature	Estimation	Completed	For Level 2
Recruiting	3	X	X
Enemy Orb	5	X	X
Treasures on Orb	1	X	X
Sealed Doors	2	X	X
Multiple Floors	3	X	X
Connector Cross Fade	1	X	X
Cue System	10	X	X
Dialog Word Wrapping	1	X
Subtotal	26

Tomb / Town	Estimation	Completed	For Level 2
Recruitable NPCs	3	X	X
Inner Tomb Fire Pit	1	X	X
Inner Tomb Shrouds	2
Subtotal	6

Data	Estimation	Completed	For Level 2
Armor Data	5
Accessory Data	5
Battle Data	5
Consumable Data	3
Shop Data	5
Weapon Data	5
Subtotal	28

Character	Estimation	Completed	For Level 2
Lead / Sword	3	X	X
Ninja / Katana	3	X	X
Wizard / Rod	3	X	X
Cleric / Archer	3	X	X
Conjuror / Rod	3	X	X
Assassin / Bare (N/A)	N/A	N/A	N/A	Physical attacker / steal / mixes two items, either doubles the power or produces a new effect (curative or offensive). Defending increases counter rate.
Subtotal	15

Level Designs	Estimation	Completed	For Level 2
Level 1 (Castle)	4	X	X
Level 2	4		X
Level 3	4
Level 4	4
Level 5	4
Level 6	4
Level 7	4
Level 8	4
Level 9	4
Subtotal	36

Narrative Encoding	Estimation	Completed	For Level 2
Level 1 (Castle)	10		X
Level 2	10		X
Level 3	10
Level 4	10
Level 5	10
Level 6	10
Level 7	10
Level 8	10
Level 9	10
Subtotal	90

Total	201

## Battle
Feature	Estimation	Completed	For Level 2
Damage Flash	1		X
Purify / Revive / Ether Items	2	X	X
Tiled Background	1	X	X
Enemy Spawns	3		?
Enemy Item Drops	1	>	X
Counter Attacking	2	>	X
Subtotal	10

Effect	Estimation	Completed	For Level 2
Defense (Plus)	1		X	75% Block (Bryan will implement)
Defense (Counter)	1		X	50% Block, Increased Counter Rate (Bryan will implement)
Defense (Trance)	1		X	50% Block, Add TP in proportion to Damage Received (Bryan will implement)
Critical	1	X	X	This needs to be done with new art. It can be similar to what’s already there or be something else. Basically, it just needs to look like an extra hard strike.
Slash	1	>	X	Attack enemies on a line.
Dark Critical (Dark)	1	>	X	This should look like the Critical Strike, but even more powerful.
Cyclone	1	>	X	Attack enemies in a radius.
Dark Slash (Dark)	1			Like Slash but with Dark element.
Double Critical (Dark)	1			Like Power Critical, but has two attack animations. Dark color theme.
Dark Cyclone (Dark)	1			Similar to Cyclone but with Dark element.
Triple Critical (Dark)	1			Like Power Critical, but has three attack animations. Dark color theme.
Power Cut	1	X	X	1.5x attack.
Sneak Cut	1	>	X	Attack enemy while applying Evasion buff to self. Looks like - https://youtu.be/XSoHSGRyNPo?t=382
Double Cut	1	>	X	2x attack.
Mantra Slash	1			Hits target with attack and splashes a small fraction of damage to all other enemies.
Triple Cut	1			Hits target enemy and two enemies at random.
Provoke Cut	1	>	X	Attack enemy and inflict Provoke.
Quad Cut	1			Hits target enemy and three enemies at random.
Soul Slash	1			Like Mantra Slash but more powerful.
Fire	1	X	X	Attack a single target with fire. Looks like - https://youtu.be/IrmDrlgTr3Y?t=264
Flame	1		X	Attack enemies on a line with a flame. Looks like - https://youtu.be/IrmDrlgTr3Y?t=246
Ice	1	X	X	Attack a single target with ice. Looks like - https://youtu.be/XSoHSGRyNPo?t=176
Snowball	1		X	Attack enemies on a vertical line with a giant snowball rolling downward.
Bolt	1	X		Attack a single target with a lightning bolt. Similar to existing effect, but will use the new graphics (Bryan will implement).
Bolt Beam	1			Attack enemies on a horizontal line with a powerful beam of electricity.
Stone	1			Attack a single target with falling stones. Looks like - https://youtu.be/XSoHSGRyNPo?t=1061
Quake	1			Attack random enemies with an earth attack. Looks like - https://youtu.be/HvD_D1gS02c?t=164
Aura	1	X	X	Raise all allies hit points a decent amount. Looks like - https://youtu.be/XSoHSGRyNPo?t=97
Empower	1	X	X	Apply Power buff to target.
Enlighten	1	X	X	Apply Magic buff to target. Looks like - https://youtu.be/IrmDrlgTr3Y?t=285
Protect	1	X	X	Apply Re-Life to target character.
Haste	1			Apply Haste to target ally. Looks like - https://youtu.be/IrmDrlgTr3Y?t=193 . Look in Art\Archives\FinalBossBlues\pixel_animations_gfxpack.zip\pixel_animations_gfxpack\animationsheets\clock.png for graphics.
Blessing	1			Applies all buffs from target ally to other allies.
Revive	1			Revive target character with full health.
Lumina (Holy)	1			Holy damage on all enemies. Very expensive.
Weaken	1	X	X	Afflict target enemy with Power Down status.
Muddle	1	X	X	Afflict target enemy with Magic Down status.
Conjure Ifrit	2		X	Summon Ifrit for Fire damage on all enemies. Very expensive. All summons use the Tarot graphics to bring in the monster. See the tarot animation preview here – Art\Archives\FinalBossBlues\pixel_tarot_deck.zip\pixel_tarot_deck\animation_preview.gif . Looks like - https://youtu.be/HvD_D1gS02c?t=104
Slow	1	X	X	Afflict target enemy with Slow status. Looks like - https://youtu.be/XSoHSGRyNPo?t=307
Conjure Shiva	2			Summon Shiva for Ice damage on all enemies. Very expensive. Looks like - https://youtu.be/XSoHSGRyNPo?t=461
Infect	1			Apply all debuffs from target enemy to other enemies.
Conjure Lich	2			Summon Lich for Dark damage on all enemies and inflicts Shield Down. Very expensive.
Conjure Archangel	2			Revive all characters, apply medium cure, and applies protect status. Very expensive.
Subtotal	47

Enemy	Estimation	Completed	For Level 2
Blue Goblin	2	X	X
Poison Goblin	2	X	X
Fire Goblin	2	X	X
Armoros	2	X	X
?	2		X
?	2		X
?	2		X
?	2		X
?	2		X
44 More Enemies	88
Subtotal	106

Total	163

Dark Tornado (Dark)	1			Hits enemies in radius. Looks like - https://youtu.be/IrmDrlgTr3Y?t=571
Gravity Crush (Dark)	1			High damage, criticals all, extremely expensive to use. Not sure what this looks like yet. Some sort of gravity bomb?

To Half Enable Jinn, give each enemy Dark weakness.
To Half Enable Jinn, give each enemy Dark resistance.
To Enable Mael, give each enemy an available elemental weakness.
To Disable Mael, give each enemy all Fire, Ice, and Lit resistance.
To Enable Shade, give each enemy Dark resistance and physical weakness.
To Disable Shade, give each enemy Dark weakness and physical resistance.
To Enable Peric, give enemies lots of AoE attacks and Shield buffs.
To Disable Peric, well, you can’t really.
To Enable Riain, give each enemy Power / Magic buffs.
To Disable Riain, give each enemy all Fire, Ice, and Dark resistance.

## Deployment
Deployment	Estimation	Completed
Windows	10
iOS	10
Android	10

Total	30

## GrandTotal
Grand Total	430

## Bugs
Title	Priority (Very Low, Low, Medium, High, Very High)	Description
Buy / Sell Excess Real Estate Graphic	Low
Graphics for Various Button Sizes	Low	Also need new art for all dialogs.
Hop Animation is Choppy	Low	Fixed with work-around but need to use Effect separate from entity to get rid of the current timing hack.
Replace Button and Dialog Graphics	Medium
Shop Confirm Menu Not Centered	Low
Battle Re-Aiming Not Implemented	Medium
Stair Not Showing on Spirit Orb	Medium	This just hasn’t been implemented at all.
Field Transition Timing Off By a Frame	Low	Screen isn’t all the way faded before loading.