## Gui
Feature	Estimation (Days)	Completed
Load Screen	3	X
Ending Screen (Good)	5
Ending Screen (Bad)	5
Credits Menu	2	>
Status Menu	2	X
Party Menu	5	>	In order to do party composition, I think I'll do something simpler like a swap button on the top three characters on the existing menu, rather than having a whole party composition menu
Item Menu	2	X
Options Menu	2	>	Include VirtualScalar (1, 2, 3, or 4).
Equip Outcome Menu	2
Key Item Menu	2
Tech Menu	2	>
Buy Menu	2	X
Sell Menu	2	X
Use Menu	2	X

Total	38

## Field
Feature	Estimation	Completed
Recruiting	3	X
Enemy Orb	5	X
Treasures on Orb	1	X
Sealed Doors	2	X
Multiple Floors	3	X
Connector Cross Fade	1	X
Cue System	10	X
Dialog Word Wrapping	1	X
Subtotal	26

Tomb / Town	Estimation	Completed
Recruitable NPCs	3	X
Inner Tomb Fire Pit	1	X
Inner Tomb Shrouds	3
Subtotal	7

Data	Estimation	Completed
Armor Data	5
Accessory Data	5
Battle Data	5
Consumable Data	3
Shop Data	5
Weapon Data	5
Subtotal	28

Character	Estimation	Completed
Lead / Sword	3	X
Ninja / Katana	3	X
Wizard / Rod	3	X
Cleric / Archer	3	X
Conjuror / Rod	3	X
Assassin / Bare (N/A)	N/A	N/A	Physical attacker / steal / mixes two items, either doubles the power or produces a new effect (curative or offensive). Defending increases counter rate.
Subtotal	15

Level Designs	Estimation	Completed
Level 1 (Castle)	4	X
Level 2	4
Level 3	4
Level 4	4
Level 5	4
Level 6	4
Level 7	4
Level 8	4
Level 9	4
Subtotal	36

Narrative Encoding	Estimation	Completed
Level 1 (Castle)	10
Level 2	10
Level 3	10
Level 4	10
Level 5	10
Level 6	10
Level 7	10
Level 8	10
Level 9	10
Subtotal	90

Total	202

## Battle
Feature	Estimation	Completed
Damage Flash	1
Purify / Revive / Ether Items	2	X
Tiled Background	1	X
Enemy Spawns	3
Enemy Item Drops	1	>
Counter Attacking	2	>
Subtotal	10

Effect	Estimation	Completed
Critical	1	X	This needs to be done with new art. It can be similar to what’s already there or be something else. Basically, it just needs to look like an extra hard strike.
Slash	1	>	Attack enemies on a line.
Dark Critical (Dark)	1	>	This should look like the Critical Strike, but even more powerful.
Cyclone	1	X	Attack enemies in a radius.
Dark Slash (Dark)	1		Like Slash but more powerful and with Dark element AND INCLUDES CANCELLING.
Double Critical (Dark)	1		Like Power Critical, but has two attack animations. Dark color theme.
Dark Cyclone (Dark)	1		Similar to Cyclone but more powerful and with Dark element AND INCLUDES CANCELLING.
Triple Critical (Dark)	1		Like Power Critical, but has three attack animations. Dark color theme.
Poison Cut	1	>	Attack enemy while applying Poison sometimes. Looks like - https://youtu.be/XSoHSGRyNPo?t=382
Power Cut	1	X	1.5x attack.
Dispel Cut	1	>	Attack enemy and remove all positive statuses.
Double Cut	1	>	2x attack.
Mantra Slash	1		Hits target with attack and splashes a small fraction of damage to all other enemies.
Triple Cut	1		Hits target enemy and two enemies at random.
Serpent Slash	1		Like Mantra Slash but more powerful and inflicts Poison.
Quad Cut	1		Hits target enemy and three enemies at random.
Fire	1	X	Attack a single target with fire. Looks like - https://youtu.be/IrmDrlgTr3Y?t=264
Flame	1	>	Attack enemies on a line with a flame. Looks like - https://youtu.be/IrmDrlgTr3Y?t=246
Ice	1	X	Attack a single target with ice. Looks like - https://youtu.be/XSoHSGRyNPo?t=176
Snowball	1	>	Attack enemies on a vertical line with a giant snowball rolling downward.
Stone	1		Attack a single target with falling stones. Looks like - https://youtu.be/XSoHSGRyNPo?t=1061
Quake	1		Attack enemies on a horizontal line with an earth attack. Looks like - https://youtu.be/HvD_D1gS02c?t=164 (except horiztonal)
???	1
???	1
Cure	1	X	Raise ally hit points a good amount. Looks like - https://youtu.be/XSoHSGRyNPo?t=97
Empower	1	X	Apply Power buff to target.
Aura	1	X	Raise all allies hit points a decent amount. Looks like - https://youtu.be/XSoHSGRyNPo?t=97
Enlighten	1	X	Apply Magic buff to target. Looks like - https://youtu.be/IrmDrlgTr3Y?t=285
Protect	1	X	Apply Re-Life to target character.
Blessing	1		Applies all buffs from target ally to other allies.
Haste	1		Apply Haste to target ally. Looks like - https://youtu.be/IrmDrlgTr3Y?t=193 . Look in Art\Archives\FinalBossBlues\pixel_animations_gfxpack.zip\pixel_animations_gfxpack\animationsheets\clock.png for graphics.
Revive	1		Revive target character with full health.
Weaken	1	X	Afflict target enemy with Power Down status.
Muddle	1	X	Afflict target enemy with Magic Down status.
Slow	1	X	Afflict target enemy with Slow status. Looks like - https://youtu.be/XSoHSGRyNPo?t=307
Bolt	1	X	Attack a single target with a lightning bolt. Similar to existing effect, but will use the new graphics (Bryan will implement).
Contagion	1		Apply all debuffs from target enemy to other enemies.
Conjure Ifrit	2	>	Summon Ifrit for Fire damage on all enemies. Very expensive. All summons use the Tarot graphics to bring in the monster. See the tarot animation preview here – Art\Archives\FinalBossBlues\pixel_tarot_deck.zip\pixel_tarot_deck\animation_preview.gif . Looks like - https://youtu.be/HvD_D1gS02c?t=104
Conjure Ramuh	2		Summon Rumah for Lightning damage on all enemies. Very expensive. All summons use the Tarot graphics to bring in the monster. See the tarot animation preview here – Art\Archives\FinalBossBlues\pixel_tarot_deck.zip\pixel_tarot_deck\animation_preview.gif .
Conjure Tiamat	2		Summon Tiamat for damage on all enemies and inflicts Shield Down. Very expensive.
Subtotal	43

Enemy	Estimation	Completed
Blue Goblin	2	X
Poison Goblin	2	X
Fire Goblin	2	X
Armoros	2	X
?	2
?	2
?	2
?	2
?	2
44 More Enemies	88
Subtotal	106

Total	159

Dark Tornado (Dark)	1		Hits enemies in radius. Looks like - https://youtu.be/IrmDrlgTr3Y?t=571
Gravity Crush (Dark)	1		High damage, criticals all, extremely expensive to use. Not sure what this looks like yet. Some sort of gravity bomb?

Bolt Beam	1		Attack enemies on a horizontal line with a powerful beam of electricity.

## Deployment
Deployment	Estimation	Completed
Windows	10
iOS	10
Android	10

Total	30

## GrandTotal
Grand Total	429

## Bugs
Bug / Todo	Priority (Very Low, Low, Medium, High, Very High, Todo, * = ASAP)	Description
Save Effect Notice	Medium	Tell the player stats are restored and game is saved.
Counter Attack Notice	Medium
Any exp gain after max level might always give lvl up message after battle.	Medium
Separate DU Names with Spaces in Text	Medium
Top and bottom of button corners are rounded inconsistently.	Low
Limit Enemies to Techs they have TP for	Low	Be careful to handle the case where they have a Tech command in queue but then lose the TP to cast it!
Item Display shows page buttons even when they don’t show anything more.	Low
Hop Animation was Choppy	Low	Fixed with work-around but need to use Effect separate from entity to get rid of the current timing hack.
Credits for Sound Effects	Low
Buy / Sell Excess Real Estate Graphic	Low
Avatar Physics Retain Momentum when Entering Menu	Low	This could be used to evade enemies for those sufficiently inclined (speed runners, etc).
Enemy hop back sometimes starting from wrong side?	Low
Make Ally button in menus into Toggles	Todo	For a more radio button style of effect.
Implement AllTarget Techs for Enemies	Todo	Like Chrono Trigger’s Lightning 2, etc.
Implement Enemy Behavior DSL	Todo
Implement Counter Attacks for Enemies	Todo
Implement Drain Techs	Todo
Implement Gravity (Percentage) Techs	Todo
Implement Shroud for TombInners	Todo
Implement Silence Sleep Confuse.	Todo*	Confuse will only have an effect on allies. Silence and Sleep only partially implemented.
Implement back drop for fill bar	Todo
Add checksum to Save File.	Todo
Balance all songs in the game.	Todo
Balance all sounds in the game.	Todo
Implement Quit button in Options.	Todo